## Gantt Chart Template
Gantt Chart Template
Project Name: | teledoctor
| Task +B7:E35Name | Start (Date) | End (Date) | Duration (Days)
| Gather Data | 2023-01-01 | 2023-01-10 | 9
| Develop Project Charter | 2023-01-01 | 2023-01-19 | 18
| Obtain Project Charter Approval | 2023-01-02 | 2023-01-28 | 26
| Identify Stakeholders | 2023-01-30 | 2023-02-04 | 5
| Analyze Stakeholders | 2023-02-12 | 2023-02-25 | 13
| Define Project Scope | 2023-02-19 | 2023-02-28 | 6
| Develop Scope Statement | 2023-03-09 | 2023-03-15 | 6
| Define Activities | 2023-03-10 | 2023-03-11 | 1
| Sequence Activities | 2023-03-13 | 2023-04-09 | 27
| Estimate Activity Duration | 2023-04-14 | 2023-05-20 | 36
| Develop Schedule | 2023-05-15 | 2023-07-16 | 62
| Cost Planning | 2023-07-16 | 2023-07-21 | 5
| Identify Resources | 2023-07-22 | 2023-07-30 | 8
| Begin Frame | 2023-08-10 | 2023-08-20 | 10
| Risk Planning | 2023-08-21 | 2023-08-26 | 5
| Communication Planning | 2023-08-26 | 2023-08-30 | 4
| Model Training | 2023-09-01 | 2023-09-10 | 9
| Platform Development | 2023-09-12 | 2023-09-20 | 8
| Integrate DoctorPad Application | 2023-09-21 | 2023-09-30 | 9
| Implement Doctor-Patient Communication Features | 2023-10-01 | 2023-10-10 | 9
| Conduct System Testing | 2023-10-11 | 2023-10-18 | 7
| Perform User Acceptance Testing (UAT) | 2023-11-22 | 2023-11-29 | 7
| Training and Education | 2023-12-02 | 2023-12-10 | 8
| Project Performance Monitoring | 2023-12-12 | 2023-12-20 | 8
| Risk Monitoring and Control | 2023-12-21 | 2023-12-25 | 4
| Quality Monitoring | 2023-12-25 | 2023-12-28 | 3
| Complete Project Documentation | 2023-12-28 | 2023-12-29 | 1
| Conduct Lessons Learned Session | 2023-12-29 | 2023-12-30 | 1

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!