## Task List
| Project Name | TELEDOCTOR
| Project Manager | Mahnoor
| Date | june 2023-2024
Version
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Task No. | Task Description | Task Owner | Dependency | Resources Needed | Task Status | Cost | Start Date | Estimated Completion | Finish Date | Notes
1 | Initiation Phase
1.1 | First we collect the dataset for three skin diseases. | mahnoor and fizza | data collection |  | Complete |  | 2023-01-02 | 9day | 2023-01-10
1.1.1 | Developing a detailed document for project scope , project goal, project overview, | ameema | project plaining |  | Complete |  | 2023-01-01 | 18day | 2023-01-19
1.1.2 | Develop the project schedule. | mahnoor | team setup |  | Complete |  | 2023-01-02 | 26day | 2023-01-28
1.1.3 | Identify key stakeholders. | fizza | objectives and scope |  | Complete |  | 2023-01-30 | 5day | 2023-02-04
2 | Planning Phase
2.1 | Create a detailed project plan. | ameema | project plan |  | Complete |  | 2023-03-09 | 6day | 2023-03-15
2.1.1 | Create Work Breakdown Structure (WBS) | fizza | project plan |  | Complete |  | 2023-03-10 | 1day | 2023-03-11
2.1.2 | Schedule Planning: | mahnoor | prepare gant chart |  | Complete |  | 2023-03-13 | 27day | 2023-04-09
2.1.3 | Cost Planning: | mahnoor | project plan |  | Complete |  | 2023-07-16 | 5day | 2023-07-21
2.2 | Resource Planning: | fizza | gather requirements |  | Complete |  | 2023-07-22 | 8day | 2023-07-30
2.2.1 | Risk Planning: | mahnoor | project plan |  | Complete |  |  | 6day
2.2.2 | Communication Planning: | ameema | system plan |  | Complete |  |  | 6day
3 | Execution Phase
3.1 | Model Training: | ameema | dataset , algorithm |  | inprogress |  | 2023-09-01 | 9day | 2023-09-10
3.2 | Platform Development: | fizza | develop application | frameworks ,tools | Complete |  | 2023-09-12 | 8day | 2023-09-20
3.2.1 | Develop TeleDoctor Platform | fizza | platform requirements |  | Complete |  | 2023-09-21 | 9day | 2023-09-30
3.2.2 | Integrate DoctorPad Application | mahnoor | graphics tablet | graphics tablet | Complete | 11000 | 2023-10-01 | 9day | 2023-10-10
3.2.3 | Implement Doctor-Patient Communication Features | ameema | database sturcture |  | Assigned |  | 2023-10-01 | 9day | 2023-10-10
4 | Control Phase
4.1 | Risk Monitoring and Control: | ameema | data security |  | Assigned |  | 2023-10-11 | 7day | 2023-10-18
4.2 | Quality Monitoring | mahnoor | define quality of application |  | Assigned |  | 2023-11-22 | 7day | 2023-11-29
4.3 | Change Control: | fizza | any change if needed |  | Assigned |  | 2023-12-02 | 8day | 2023-12-10
4.4 | Testing: | ameema | implement QA |  | Assigned |  | 2023-11-22 | 7day | 2023-11-29
5 | Close Phase
5.1 | Project Closure: | mahnoor | closing |  | Assigned |  | 2023-12-02 | 8day | 2023-12-10
5.1.1 | Complete Project Documentation | fizza | documentation and reporting |  | Assigned |  | 2023-12-12 | 8day | 2023-12-20
5.1.2 | Conduct Lessons Learned Session | ameema | system deployment |  | Assigned |  | 2023-12-21 | 8day | 2023-12-25
5.1.3 | Close Project Procurements | mahnoor and fizza | deliverables |  | Assigned |  | 2023-12-28 | 3day | 2023-12-30

## WBS Tree
WBS TREE Diagram
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## How to Use WBS Template
How to Use Our WBS Template
The following is a breakdown of the terms and sections in the task list and WBS template.
Task No.: This is a numerical listing of the deliverable, which is further distinguished as you drill down deeper from task to subtask by decimal points to make sure you know exactly where in the process you are.
Task Description: This section details what the deliverable is and also goes into the task and the subtasks necessary to complete it.
Task Owner: Every deliverable, task and subtask needs an owner to make sure the work is getting done, and that person is noted in this column.
Dependency: Some tasks cannot be started until the task before them has been completed, which means it’s dependent on that task and they should be linked. This is the space where you can note task dependencies.
Resources Needed: Whatever the task needs in terms of people, equipment, materials, etc., is listed here.
Task Status: This is where you can track the status of a specific task or subtask. The dropdown menu gives you the option of marking the task as unassigned, assigned, in progress, late or complete.
Cost: Note the financial commitment needed to get the deliverable done.
Start Date: When did work on the deliverable begin? Mark it here.
Estimated Completion: The estimated amount of time allotted for the completion of the deliverable should be noted here.
Finish Date: When the deliverable is done, note the end date here.
Using the Tree Diagram
On the second sheet there is a tree chart to visualize the work breakdown structure, from the highest level at the top to the lowest level at the bottom, where the bottom is more specific and the top more general. You don’t have to add all the extra data you filled into the previous sheet, just the deliverable, task and how every many subtasks are needed to get the work done.